## Slide 1
▍ TECH ROADMAP
2026-05-13
# ROADMAP-FY27
Four-quarter platform roadmap with explicit Q3 freeze
Three architectural bets, one mandated freeze window, four named owners.
VERDICT
GO
Lock the four-phase architecture plan. Q3 has a hard merge-freeze 2026-09-15 → 2026-10-01 for the multi-tenant migration. Engineering capacity is 14 FTE — plan holds within 88% utilisation.
Chief Architect · arch@zimablueai.com
ADR-FY27-001

## Slide 2
▍ CAPACITY · CONSTRAINTS
$
What we're spending against
Capacity, not roadmap items, is the binding constraint. These six numbers shape every decision below.
Eng FTE total
14
target 14
+2 hired Q1
Senior:Mid:Junior
4:7:3
1 senior departing Q4
Runway after FY27
18
mo
target 12
post Series-A
Avg PR lead time
31
h
target 24
+ 4h vs Q1
Bug backlog
47
target 30
see retro
Build success rate
94
%
target 95
flaky 1.x suite

## Slide 3
▍ FOUR-PHASE PLAN
$
Q3 → Q2 next year
Each phase has a named owner (M. Wei / P. Singh / L. Park / J. Wu). Q3 freeze is non-negotiable.
Q3 26
Jul–Sep
Multi-tenant migration
Merge freeze 09-15→10-01
Owner: M. Wei
Q4 26
Oct–Dec
Event-driven inbox rewrite
Search relevance v2
Owner: P. Singh
Q1 27
Jan–Mar
Open SDK GA
OAuth marketplace
Owner: L. Park
Q2 27
Apr–Jun
EU region launch
SOC 2 Type II audit
Owner: J. Wu

## Slide 4
▍ RISKS · MITIGATIONS
$
Five risks worth tracking
Every risk has a named owner and a due date — no "team" entries.
RISKS
Senior departure mid Q4
owner of inbox rewrite leaves
HIGH
Q3 freeze slips past 10-01
blocks event-driven rewrite start
HIGH
EU data residency in Q2
may require dedicated infra
MED
Build flakiness on 1.x suite
merge throughput at 87%
MED
SOC 2 evidence collection
estimate +3wk in Q2
LOW
MITIGATIONS
Knowledge-transfer plan + retention bonus
owner: P. Singh
Aug 30
Hard cut-over 10-01 with rollback gate
owner: M. Wei
Sep 28
Lock GCP-Frankfurt region by Mar 15
owner: L. Park
Mar 15
Migrate 1.x suite to Pytest in Q4
owner: DevTools
Dec 01
Engage Drata + evidence-collector subcontractor
owner: J. Wu
Apr 15

## Slide 5
▍ BINDING DECISIONS
$
Five actions, four owners, one binding vote
Approve item 1 today; items 2–5 unlock automatically with named owners.
#
ACTION
OWNER
DUE
STATUS
01
Approve four-phase plan + Q3 freeze window
binding architecture vote
Engineering Council
May 20
TODO
02
Lock GCP region for EU residency requirement
L. Park
Mar 15
TODO
03
Migrate 1.x test suite to Pytest
DevTools
Dec 01
TODO
04
Engage Drata + evidence-collector for SOC 2
J. Wu
Apr 15
TODO
05
Quarterly checkpoint review (every Mar / Jun / Sep / Dec)
Chief Architect
ongoing
TODO