## Slide 1
▍ SPRINT DEV REPORT
2026-05-13
# SPRINT-W22
W22 sprint — velocity green, quality amber, two blockers
Shipped 18 of 22 story points. Two blockers required engineering escalation. Quality gate slipped on the inbox refactor.
VERDICT
HOLD
Hold on scope for W23 (carry over the 4 unshipped points; do NOT add new). The quality regression on inbox is a real signal — fix the gate before resuming.
Dev Lead · dev@zimablueai.com
PR-batch W22

## Slide 2
▍ W22 OUTCOMES
$
Six dev KPIs
Velocity at plan, quality dropped, customer-reported issues stable.
Story points shipped
18 / 22
carry to W23
PRs merged
47
above plan
Avg PR lead time
34
h
review queue
P1 bugs in prod
3
target 2
inbox refactor leaked
Build success rate
92
%
1.x flakes
On-call MTTR
44
min
target 60
good

## Slide 3
▍ WORKED / DIDN'T / CHANGE
$
Three keepers, two drops, three changes
Sprint retro distilled to actionable diff.
WORKED
Pair on first PR of every refactor
caught 2 design issues early
Async standup format (Slack thread)
saved 3.5h across team this week
Daily SLO dashboard in #ops
spotted MTTR drift Day 2
DIDN'T
Inbox refactor quality gate optional
skipped under deadline → 3 P1s
Late-Friday merges (3 of 18 PRs)
1 caused weekend page
CHANGE
Quality gate becomes hard CI block
starts W23 day 1
Friday 14:00 deploy freeze
VP sign-off to override
Pair review for any refactor > 200 LOC
starts W23

## Slide 4
▍ W23 ACTIONS
$
Four actions, three owners
#
ACTION
OWNER
DUE
STATUS
01
Enforce coverage-70% block in CI for refactor PRs
DevTools · A. Lin
W23 Mon
TODO
02
Migrate 1.x flaky tests to Pytest (15 of 47 files)
DevTools · A. Lin
W26 Fri
TODO
03
Set up Friday 14:00 deploy-freeze guard in release bot
Release · P. Chen
W23 Wed
TODO
04
Pair review process doc + Slack reminder
EM · S. Wong
W23 Fri
DONE